## Sheet1
Defect ID | Title | Description | Severity | Priority | Status | Module | Detected In Version | Assigned To | Reported By | Reported Date | Environment | Steps to Reproduce | Expected Result | Actual Result | Attachments | Comments
BUG-001 | No option available to cancel an order | Users cannot cancel an order from the "My Orders" section. | Major | High | Open | Order Management | v1.0 | Dev Team | - | 2025-03-25 | Staging | 1. Log in to the Craftify platform. 2. Navigate to "My Orders" section. 3. Select an active order. 4. Observe that there is no option to cancel the order. | Users should be able to cancel an order from the "My Orders" section. | No cancel option is available. | N/A | Requires an update to include the order cancellation feature.
BUG-002 | Users can manually modify the product price | Users can intercept and modify the price value in the request payload before checkout. | Critical | High | Open | Payment & Checkout | v1.0 | Dev Team | - | 2025-03-25 | Staging | 1. Log in as a user and browse any product. 2. Add product to cart and proceed to checkout. 3. Intercept request using Burp Suite. 4. Modify the product price in the request payload. 5. Forward the request and complete the order. | System should validate and prevent unauthorized price modifications. | System allows manual price modifications without validation. | N/A | Requires validation mechanism for product pricing.
BUG-003 | Orders can be placed without completing payment | Orders are getting placed even when the online payment is incomplete. | Critical | High | Open | Payment & Checkout | v1.0 | Dev Team | - | 2025-03-25 | Staging | 1. Add items to cart and proceed to checkout. 2. Choose online payment method (RazorPay). 3. Close the payment gateway window before completing the transaction. 4. Check "My Orders" section. | Orders should only be placed after a successful payment transaction. | Orders are placed even when the payment is not completed. | N/A | Requires validation to ensure payment completion before order placement.
BUG-004 | The system allows PDF files to be uploaded as product images | Admin users can upload non-image files (PDF) in the product image upload section. | Major | Medium | Open | Product Management | v1.0 | Dev Team | - | 2025-03-25 | Staging | 1. Log in to the admin portal. 2. Navigate to "Add Items" section. 3. Click "Upload Image" option. 4. Select a PDF file instead of an image. | System should restrict non-image files from being uploaded as product images. | System allows uploading of PDF files as product images. | N/A | Needs file format validation to allow only image files.
BUG-005 | "My Profile," "Subscribe," and "Explore Jobs" buttons are inaccessible | Certain UI buttons are unresponsive when clicked. | Minor | Low | Open | UI/UX | v1.0 | Dev Team | - | 2025-03-25 | Staging | 1. Log in to the Craftify platform. 2. Navigate to the homepage or relevant section. 3. Click "My Profile," "Subscribe," and "Explore Jobs" buttons. | Buttons should navigate to their respective sections/pages. | Buttons are unresponsive and do not navigate anywhere. | N/A | Requires UI/UX fix to make buttons functional.